## Project Plan
Jumpy Street
Group A: Lauren Kelly, Lucas Mills, Andrew Jennings
Features and Description | Estimated Implementation | Assigned To | Status
Not Implemented
In Progress
Done
Set up all branch/project plan/accounts/etc | 2019-09-18 | Lauren | Completed
Pick out and add model and sound assets | 2019-09-23 | Lucas | In Progress
Write down game plan for how we will break up gameplay code | 2019-09-18 | Lucas | Completed
Create Unity project and basic menu skeleton | 2019-09-18 | Andrew | Completed
Menu/UI programming | 2019-09-25 | Andrew | In Progress
Procedural code | 2019-09-25 | Lucas | In Progress
Movement | 2019-09-25 | Lauren | Completed
Raycasting obstacles | 2019-10-02 | Lauren | Not Implemented
Score/High Score |  |  | Not Implemented
Death conditions |  |  | Not Implemented
Lighting |  |  | Not Implemented
Sound effects |  |  | Not Implemented
Pickups |  |  | Not Implemented
Make our own assets |  |  | Not Implemented
Insert a row above to add more features to the list.