## Project Plan
Jumpy Street
Group A: Lauren Kelly, Lucas Mills, Andrew Jennings
Features and Description | Estimated Implementation | Assigned To | Status
Not Implemented
In Progress
Done
Set up all branch/project plan/accounts/etc | 2019-09-18 | Lauren | Completed
Pick out and add model and sound assets | 2019-09-23 | Lucas | Completed
Write down game plan for how we will break up gameplay code | 2019-09-18 | Lucas | Completed
Create Unity project and basic menu skeleton | 2019-09-18 | Andrew | Completed
Tile generation | 2019-09-25 | Lucas | Completed
Movement | 2019-09-25 | Lauren | Completed
Menu/UI programming | 2019-09-25 | Andrew | Completed
Expand tile system to prep instantiation (write water, grass, and car logic) | 2019-10-09 | Lucas | In Progress
"Max Y" global variable, informs score and camera | 2019-10-09 | Lauren | In Progress
Setting up player character animations | 2019-10-09 | Lauren | In Progress
Random instantiation | 2019-10-16 | Andrew | In Progress
Raycasting obstacles |  | Lauren | Not Implemented
Research timed event row (train) |  | Lucas | Not Implemented
High Score system |  | Lauren | Not Implemented
Death conditions |  | Andrew | Not Implemented
Update UI with high scores and details |  | Lauren/Andrew | Not Implemented
Character Customization | Touch ups | All | Not Implemented
Lighting | Touch ups | All | Not Implemented
Sound effects | Touch ups | All | In Progress
Pickups | Touch ups | Andrew | Not Implemented
Make our own assets | Touch ups | All | Not Implemented
Insert a row above to add more features to the list.